## Overview
Area | Summary | Status
Project | Humans of EV 5.0: React + Vite frontend, Express API, SQLite database. | Active local project
Purpose | Admin-managed EV news, intelligence, vehicles, business, energy, people, media, events, membership and B2B enquiries. | Scope summary
Local demo | Separate demo database with simulated email and checkout; demo servers are currently stopped. | Available when started
Navigation | Home plus Latest News, EV Intelligence, Vehicles, EV Business, Energy, People, HEV Media, Events and B2B Solutions. | Completed
Landing pages | Each of the nine non-home menu pages has four topic sections plus its page hero; public pages share header, Contact CTA and footer. | Completed
Admin and content | Admin access, editorial/media CRUD, image upload, access control, member accounts, contact and newsletter management. | Implemented
Content migration | Imported 100 News, 28 Events, 17 Magazine issues and 5 candidate CXO interviews to the demo DB; no podcasts were exposed by source API. | Demo DB only
Main database | Regular database was not used for the source content transfer. | Untouched
Video | Admin-managed videos with YouTube/Vimeo embeds and direct video file playback; page needs published video entries to show content. | Implemented; add content
Plan date | 11 October 2026. | No delivery dates or individual owners were provided

## Work Plan
Phase | Task | Plan / description | Deliverable / evidence | Status | Priority | Dependency
Foundation | Configure application | React/Vite frontend with Express API and SQLite persistence. | Local app and production build verified. | Completed | High | —
Admin | Administrator access | Protected admin sign-in, hashed passwords, session cookies and CSRF checks. | Authenticated admin routes and panel. | Completed | High | Foundation
Content CMS | Manage public content | CRUD for news, podcasts, videos, magazine and CXO profiles; image uploads, draft/published state and free/member access. | Admin tools and API-backed public content. | Completed | High | Admin
Member access | Accounts and paid access | Free member signup/sign-in, membership state and secure checkout integration. | Demo payment simulated; live payments require provider keys. | Implemented; live setup pending | High | Admin
Contact and email | Enquiries and subscriptions | Persist contact/newsletter data and provide admin review tools. | Admin inbox and API endpoints; live email requires provider setup. | Implemented; live setup pending | High | Admin
Dynamic website | Admin-managed sections | Edit navigation and structured site data such as events, plans and dashboard content. | Public pages load stored website content. | Completed | High | Content CMS
Local demo APIs | Safe local testing | Separate demo DB with sample content and simulated email/payment actions. | Dedicated demo run commands; no real charges or emails. | Completed | High | Foundation
Source content transfer | Import Humans of EV content | Preview-first importer with attribution and deduplication. | Demo DB: 100 news, 28 events, 17 magazine issues, 5 interview candidates; 0 podcasts. | Completed; demo only | High | Dynamic website
Video playback | Play published videos | Admin video records, supported inline players and database schema migration. | Updated API smoke-tested; add public URLs and publish. | Implemented; content entry needed | High | Content CMS
Navigation redesign | Use flat menu and simple sections | Add the requested 10 top-level navigation links and simple landing pages. | Desktop/mobile menu verified; shared contact, header and footer retained. | Completed | High | Dynamic website
Demo notice | Remove local banner | Remove the LOCAL DEMO notice without changing demo-mode functionality. | Banner markup removed; production build passes. | Completed | Medium | Local demo APIs
Editorial review | Review imported interviews | Check names, roles and organization details for five candidate CXO records. | Correct uncertain records in Admin before promoting them. | Recommended next step | Medium | Source content transfer
Video publishing | Add real video content | Add a YouTube/Vimeo URL or direct MP4/WebM/Ogg URL, thumbnail and description; publish. | Videos page has content after a video is published. | Recommended next step | High | Video playback
Podcast source | Supply podcast episodes | Provide a source/feed URL or create podcast entries manually in Admin. | No podcast episodes were found through the source API. | Waiting for content/source | Medium | Content CMS
Main DB migration | Decide whether to import source content to main DB | If approved, back up data/humans-of-ev.sqlite, review the preview, then explicitly apply. | Main database has not been imported. | Approval required | Medium | Source content transfer
Email provider | Enable real Brevo delivery | Configure private API key, verified sender and admin email; test end to end. | Local demo simulates email; do not expose provider secrets. | External setup pending | High | Contact and email
Payment provider | Enable real Razorpay checkout | Configure private keys securely and test with Razorpay test mode before production. | Local demo simulates payment and does not charge money. | External setup pending | High | Member access
Production readiness | Prepare deployment and final QA | Set HTTPS, production secrets and backups; validate live content, email, membership and payment flows. | Complete after external setup and editorial review. | Future pre-launch | High | Email provider; Payment provider
Admin password flow | Consider account-management enhancement | Add in-app password change/reset only if required. | Current admin account is configured through server environment on first setup. | Optional future work | Low | Admin

## Content Transfer
Content type | Source / method | Quantity | State | Details / guardrails
News | Latest public WordPress News category posts | 100 | Imported | Demo DB only; original article attribution retained.
Events | Public EV Events category posts | 28 | Imported | Saved to Events site content with source links where available.
Magazine | Public Magazine category posts | 17 | Imported | Saved as managed magazine records with source attribution.
CXO interviews | Articles identified by interview title patterns | 5 | Imported; review | Candidate profiles; verify names, roles and organizations.
Podcasts | Public WordPress API posts and media checked | 0 | Not found | No podcast content was invented; add manually or provide source URL/feed.
Images | Featured/source article images | External URLs | Linked, not downloaded | Availability depends on the source site.
Main database | Regular database import target | 0 | Untouched | Back up and get explicit approval before an import to the main DB.

## Remaining Actions
Action | Next step | Owner | Priority | Status | Notes
Add videos | Admin > Videos: add a public video URL, thumbnail and description, then publish and test playback. | Project owner | High | Ready to do | Videos page stays empty until published items exist.
Review interviews | Verify five imported CXO profiles; edit inaccurate or uncertain data in Admin. | Editorial owner | Medium | Recommended | Some records were detected by title matching.
Choose podcast source | Provide a podcast feed/episode URL or enter episodes manually in Admin. | Project owner / content team | Medium | Waiting for content | Public source API did not expose podcasts.
Configure live email | Set Brevo key and verified sender privately in server configuration; test sending. | Account owner | High | External setup | Never put secrets in frontend code or chat.
Configure payments | Set Razorpay keys securely and test using Razorpay test mode. | Account owner | High | External setup | Demo checkout does not contact Razorpay.
Approve main DB import | If wanted, back up the main DB, review importer preview and explicitly approve application. | Project owner | Medium | Decision required | No main DB import has happened.
Prepare production launch | Configure HTTPS, secrets and backups; run end-to-end checks after provider setup. | Project owner / developer | High | Future pre-launch | Depends on real provider setup and content review.
Admin password change | Decide whether to add an in-app admin password workflow. | Project owner | Low | Optional | Not currently implemented.